## Release 1.1
Ref. | Features/Enhancements | JIRA | Priority | Rank | Release | Category | Issue Type | Notes | Needs ISCIS Deployment
1 | Add 2 summary fields to UNHS Daily Report and downloaded Excel sheet | HDUF-1329 | High | 5 | 1 | UNHS Daily Report | User Story
2 | NSO auto accept works when results sent before recommendation date | HDUF-1322 | High | 5 | 1 | Recommendation | Bug
3 | Add 2 columns in the UNHS Daily Report to note a Deceased baby | HDUF-1305 | High | 5 | 1 | UNHS Daily Report | User Story
4 | SCG role missing when adding an infant to an existing family | HDUF-1316 | High | 5 | 1 | Second Caregiver | Bug
5 | Add a warning message when a duplicate Health Card Number is entered in DUNHS | HDUF-1313 | High | 5 | 1 | Health Card | User Story | Anu will check it across all agencies about the duplication of HCN with the Privacy people
6 | Need More Validation for Alternate Contact Information Name in Step1 | HDUF-1302 | High | 5 | 1 | Alternate Contact | Bug
7 | UNHS resources doesnot filter based on token org role | HDUF-1324 | High | 5 | 1 | Token filter | Bug | Linked to HDUF-1332(sub task)
8 | Add one option "Not Applicable" for the consent of Family Sharing | HDUF-1355 | High | 5 | 1 | Family Sharing | User Story
9 | Seeing the same error message multiple times | HDUF-1306 | High | 3 | 1 |  | Bug

## Backlog Items
Ref. | Features/Enhancements | JIRA | Priority | Rank | Release | Category | Issue Type | Notes | Needs ISCIS Deployment
1 | Add 2 summary fields to UNHS Daily Report and downloaded Excel sheet | HDUF-1329 | High | 5 | 1 | UNHS Daily Report
2 | NSO auto accept works when results sent before recommendation date | HDUF-1322 | High | 5 | 1 | Recommendation | Bug
3 | Add one column in the UNHS Daily Report to note a Deceased baby | HDUF-1305 | High | 5 | 1 | UNHS Daily Report | User Story
4 | SCG role missing when adding an infant to an existing family | HDUF-1316 | High | 5 | 1 | Second Caregiver | Bug
5 | Add a warning message when a duplicate Health Card Number is entered in DUNHS | HDUF-1313 | High | 5 | 1 | Health Card | User Story | Anu will check it across all agencies about the duplication of HCN with the Privacy people
6 | Need More Validation for Alternate Contact Information Name in Step1 | HDUF-1302 | High | 5 | 1 | Alternate Contact | Bug
7 | UNHS resources doesnot filter based on token org role | HDUF-1324 | High | 5 | 1 | Token filter | Bug | Linked to HDUF-1332(sub task)
8 | Add one option "Not Applicable" for the consent of Family Sharing | HDUF-1355 | High | 5 | 1 | Family Sharing | User Story
9 | Seeing the same error message multiple times | HDUF-1306 | High | 3 | 1 |  | Bug
10 | Ability to run Daily Report, NSO Inbound and NSO Outbound at Ministry Level with the TBS Report Back measures built in | HDUF-1333 | High | 5 | TBD | Reports | User Story | Need internal meeting to get it sorted out
11 | Digital UNHS >Auto CAP close | HDUF-1278 | High | 5 | 2 | CAP | User Story
12 | Digital UNHS >Auto close CAP with declined consent | HDUF-1323 | High | 5 | 2 | CAP | User Story | CAP should be closed automatically if family declines consent
13 | Search: Failed to find CR when searching with both Last Name and First name | HDUF-986 | High | 5 | 3 | Search | Bug | New requirement as Last and First names are only searched for Primary Contact currently
14 | Ability to print filled UNHS form for closed CAP | HDUF-1334 | High | 5 | 2 | UNHS Print | User Story | Requires more discussion
15 | Digital UNHS>Update on ADPOAE page | HDUF-1314 | High | 4 | 4 | ADPOAE | User Story | Current status: once it is entered and can not be edited
16 | Digital UNHS>Update on AABR page | HDUF-1315 | High | 4 | 4 | AABR | User Story | Current status: once it is entered and can not be edited
17 | Digital UNHS>ISCIS>Mandatory fields to be in sync | HDUF-1335 | High | 4 | 5 | Field Sync | User Story |  | ISCIS
18 | Digital UNHS>ISCIS>New CR added without required field (telephone number) when adding infant to an existing family | HDUF-1336 | High | 4 | 5 | Field Sync | Bug | Existing family is created in ISCIS wihtout phone number entered | ISCIS
19 | ISCIS>Birth module should be mandatory in ISCIS | HDUF-1310 | High | 4 | 5 | Field Sync | User Story
20 | CDIS>Digital UNHS>Recommended Date changes | HDUF-1337 | High | 3 | 6 | Recommendation | User Story | Recommended Date for ADPOAE and AABR, need redesign and thinking | ISCIS
21 | Digital UNHS>Next steps should automatically create Recommendations in ISCIS | HDUF-1338 | High | 3 | 6 | Recommendation | User Story | Same as the one above CI-10
22 | API - [Regression][D-UNHS] - Unmatched records are displayed from the Provider Individual Search | HDUF-1250 | Medium |  |  | Provider individual search | Bug | Fixing status
23 | Digital UNHS>Infant's Healthcare Provider to be allowed to enter on the fly | HDUF-1339 | Medium |  |  | Healthcare Provider | User Story | Part of CDIS moderizaton session, it will be long term conseration for DUNHS
24 | Digital UNHS>Infant's Primary Healthcare provider>Pick latest if there are multiple | HDUF-1340 | Medium |  |  | Healthcare Provider | Bug
25 | Infant should show up in one row when multiple ADPOAE/AABR exists | HDUF-1341 | Medium |  |  | UNHS Daily Report | Bug
26 | All notes to be saved under CR details and displayed under Care Recipient Notes in D-UNHS | HDUF-1342 | Medium |  |  | Notes | User Story | Questions in the user story
27 | Digital UNHS>Adding Branch drop-down for user on the home page | HDUF-1343 | Medium |  |  | Affiliation | User Story | Implemented for DUNHS enhancements or CDIS implementation?
28 | UI - No reset option to unselect optional radio buttons | HDUF-829 | Medium |  |  | Reset radio button | Bug | Primary contact page (Parent, Legal Guardian)
29 | API - Care team API does not filter based on token org role | HDUF-1155 | Low |  |  | Token filter | Bug | Fixing status
30 | Digital UNHS>Allow open CAP to be accessed in other regions | HDUF-1344 |  |  |  | CAP | User Story | Policy input is required
31 | Allow multiple active IH CAP in different regions | HDUF-1319 |  |  |  | CAP | User Story | Policy input is required
32 | Digital UNHS>Review info before hit submit | HDUF-1349 | Nice to have |  |  | Review | User Story | Double check whether it is really needed for now as there is Edit functionality already on the form
33 | Digital UNHS>ISCIS>Next steps to be displayed on Summary page of the CR | HDUF-1347 | Low |  |  |  | User Story | Linked to HDUF-1338
34 | [UAT Bug] 2 stage 1 is created with different status when user sets AOE date after AABR date | HDUF-1262 |  |  |  |  | Bug | wait for Qing's test result, if it is not fixed, it will be put into Release 1
35 | Missing Screener Details Checkbox Selection in Reviewed ADPOAE and AABR Forms | HDUF-1320 | Low |  |  |  | Bug | Assigned to Sanjay
36 | Digital UNHS>Download and Print>Change the way the risk factors are recorded | HDUF-1318 | Low |  |  |  | User Story | Anu will get back on it. Quite ok to have form in 2 pages with bigger fonts
37 | Add extension field for Alternate Phone Number | HDUF-1312 | Low |  |  |  | User Story
38 | Digital UNHS>ISCIS>Multiple birth details should be mentioned in Summary tab in ISCIS | HDUF-1309 | Medium |  |  |  | User Story
39 | Error Message Displayed When 'Did Not Test' Suboptions Left Unselected | HDUF-1301 |  |  |  |  | Bug | Sanjay will investigate it, "Other" option should be mandatory
40 | UNHS NSO report time values have inconsistent format | HDUF-1286 | Medium |  |  |  | Bug
41 | Error Handling for 'Transferred to' or 'Other' Checkbox Selection on ADPOE/AABR Page | HDUF-1351 |  |  |  | ADPOAE/AABR | Bug
42 | UNHS report not showing latest changes to record in same session | HDUF-1350 | Low |  |  | UNHS Daily Report | Bug
43 | NSO phase 2 ->UNHS token can be used in POST call via NSO | HDUF-1326 | Low
44 | NSO>Deal with different Patient IDs for the same child | HDUF-1303 | [5 empty] | Anu and Frank will discuss about it
45 | UNHS- ADPOE/AABR - The blank page will be created only for first record and when user click create one button | HDUF-1284 | Low
46 | Add a column to Search results to indicate whether the family is shared | HDUF-1359 |  |  | 2 |  |  | Search
47 | NSO Outbound Report has no response for a specific date | HDUF-1358
48 | ISCIS>Make Suspected Biomedical Conditions non-mandatory in the PPC Form | HDUF-1382
49 | Digital UNHS>Add a column for Step 2 Care Recipients Notes to the CDIS Daily reports | HDUF-1330 | High |  |  | UNHS Daily Report | User Story | Put Next step in the Notes but not in the report
Requirement Pending
Partial Requirement Provided
Ready to for development
Front-end/ISCIS
Front-end
11 | Digital UNHS >Auto CAP close | HDUF-1278 | High | 5 | 2 | CAP | User Story
12 | Digital UNHS >Auto close CAP with declined consent | HDUF-1323 | High | 5 | 2 | CAP | User Story | CAP should be closed automatically if family declines consent
13 | Search: Failed to find CR when searching with both Last Name and First name | HDUF-986 | High | 5 | 3 | Search | Bug | New requirement as Last and First names are only searched for Primary Contact currently
21 | Digital UNHS>Next steps should automatically create Recommendations in ISCIS | HDUF-1338 | High | 3 | 6 | Recommendation | User Story | Same as the one above CI-10